## Schedule
Capstone Project Enhanced AI Physical Rehabilitation
Project:
|  |  | Last Updated: | 2024-04-30
|  |  | Year | 2023 | [16 empty] | 2024
|  |  | Month | Sept |  |  |  | Oct |  |  |  |  | Nov |  |  |  | Dec |  |  |  | Jan |  |  |  |  | Feb |  |  |  | Mar |  |  |  | Apr |  |  |  | May
| Task Description | Due | Assigned | 2018-09-03 | 2018-09-10 | 2018-09-17 | 2018-09-24 | 2018-10-01 | 2018-10-08 | 2018-10-15 | 2018-10-22 | 2018-10-29 | 2018-11-05 | 2018-11-12 | 2018-11-19 | 2018-11-26 | 2018-12-03 | 2018-12-10 | 2018-12-17 | 2018-12-24 | 2018-12-31 | 2019-01-07 | 2019-01-14 | 2019-01-21 | 2019-01-28 | 2019-02-04 | 2019-02-11 | 2019-02-18 | 2019-02-25 | 2019-03-04 | 2019-03-11 | 2019-03-18 | 2019-03-25 | 2019-04-01 | 2019-04-08 | 2019-04-15 | 2019-04-22 | 2019-04-29 | 2019-05-06 | 2019-05-13 | 2019-05-20 | 2019-05-27
DUE DATES:
| Project Definition | Sept. 21
| Project Plan | Oct. 3
| Snapshot Day #1 | Oct 10.
| Concept Design Review | Nov. 10
| Snapshot Day #2 | Dec. 5
| Project Portfolio | Dec. 8
| Engineering Release Review | Feb. 16
| Snapshot Day #3 | Mar. 27
| UI Design Expo | Apr. 26
| Design Report | 2023-05-04
Project Milestones:
| Read and Understand Project Background and Research Papers | 2023-10-01
| Explore Skeletal Extraction Models | 2024-10-01
| Extract Skeletal Joints from a Picture | 2024-10-10
| Extract Skeletal Data from an MP4 | 2023-11-10
| Write OpenPose Skeletal Data to a CSV file format | 2024-11-10
| Input deep squat exercise into MotionGPT | 2024-12-21
| Analyze Videos from the UI-PRMD Database through OpenPose | 2024-02-15
| Alter SpatioTemporal Model to analyze OpenPose Data Input | 2024-03-25
| Alter SpatioTemporal Model to analyze Kinect and Vicon Positional Data as Input | 2024-03-25
| Data Preprocessing | 2024-03-25
| Predict quality scores for the individual repetitions for Exercise 1 - Deep Squat (SpatioTemporal). | 2024-04-01
| Predict quality scores for the individual repetitions for Exercise 1 - Deep Squat (Recurrent Neural Network). | 2024-04-01
| Predict quality scores for Exercise 1 - Deep Squat (Kinect). | 2024-04-01
| Predict quality scores for Exercise 1 - Deep Squat (Vicon). | 2023-04-01
| Record several videos for exercises with a cell phone and test models. | 2023-04-20
| Debugging | 2024-04-26
| Predict quality scores for Inline Lunge, Standing Shoulder Abduction, Side Lunge | 2024-04-26
| Make sure model can differeniate exercises | IF TIME
| User interface | IF TIME
Green = Complete
Yellow = In Progress
Red = Behind Schedule