## DVPR Template
Senior Capstone Design
Project: | Enhanced AI Physical Rehabilitation |  | Primary Author: | Noah Rieth
Team: | Molly Meadows, Noah Rieth, Xian Gao |  | Date: | 2023-10-01
Design Validation Plan & Results (DVP&R)
Requirement | Test | Test Subject | Target Date | Result | Recommendation
Software can extract skeletal data from a video. (OpenPose, BlasePose, PoseFormerV2, Video Pose 3d) | Submit a mp4 video with an exercise being performed, and verify that a video output that matches the input is generated. | A video of a deep squat from One Drive | 2023-11-10 | 10/10 - Was able to extract skeletal information from own photos (all 25 joints) | Not PoseFormerV2 or VideoPose3D(No Access)
Software can condense output from skeletal video to a small datafile. | Software can generate a file that represents joint locations over time. | Skeletal data video | 2023-11-20 | 11-10-2024 Used the OpenPose function that Noah made to overlay dots onto the joints from each frame of a video. Want to export the data from each frame into a CSV file. | Output to a CSV file
Applying data preprocessing to the deep squat video exercise | Be able to align all joints correctly on the z axis from the skeletal data extracted from the library we select for this project. | Skeletal data of a deep squat | 2023-11-30 | Able to extract x, and y joints. Z points will either be the confidence interval or manually set to zero.
Tokenizing the deep squat skeletal data using motionGPT | Submit the skeletal data that has been preprocessed from the method above, and have it generate a motion graph | Skeletal data of a deep squat | 2023-12-21 | 1/18/2024 - downloaded some sample npy data from MotionGPT but is pretty unreadable/no documentation | Cannot figure out how to input 2D joint information to a 3D angular information system that MotionGPT uses
Our model can identify the deep squat exercise. | Submit processed datafiles from videos of people performing a deep squat. | Videos of deep squat exercises (One bad and one good) | 2023-12-01
Our Program can run within a reasonable amount of time | Time our program and see how long it takes to preprocess and ouput a prediction score for a deep squat | Video of an exercise (Measure with a stopwatch) | 2024-04-08 | Video of bad squat is processed on a CPU in (18:32) | If higher speed is needed we could process the video on the GPU server.
Prepare OpenPose Data for NN | Submit a video of a squat with good form -> no constructive feedback | Videos of exercises | 2024-02-20
Compare the quality scores by the NN models based on poses obtained by OpenPose, Kinect, and Vicon systems. | Submit a video of a squat -> labels from 3 different methods | Videos of exercises | 2024-03-01 | The training loss and validation loss of Vicon system is lower than these of Kinect system | If we need shorter training time, we recommend using Kinect system, otherwise we recommend using Vicon system.
Apply the existing models for rehabilitation evaluation developed to predict quality scores for squat, based on the estimated poses from the videos with OpenPose. | Submit a video of a squat -> labels from OpenPose | Videos of exercises | 2024-03-01 | Good Squat Accuracy - 0.9186... Bad Squat Accuracy - | Model Training is very inconsistent so the prediction labels change every time the model is retrained even on the same
Our model can recognize a perfect jumping-jack on the GPU server. | Submit a video of a jumping-jack with good form | Videos of exercises | 2024-04-01
Our model can recognize a perfect push-up | Submit a video of a push-up with good form | Videos of exercises | 2024-04-01
Our model can recognize a bad jumping-jack | Submit a video of a jumping-jack with bent arms | Videos of exercises | 2024-04-01
Our model can recognize a bad push-up | Submit a video of a push-up with uneven raising | Videos of exercises | 2024-04-01
Model Training Time |  | Submit information for the model to be trained on (time with python time function) | 2024-04-08 | Training time: 0:03:50.833147